## Current Pipeline (W Feedback)
Reviewers: Leadership: Brendan, Yazan, Emily Production: Garrett, Mariana, Felipe, Ishna PPM: Mahmoud, Martina Creative: Hannah, Matias
PROD PHASE | RESPONSIBLE | GENERAL TASK | SPECIFIC ACTIONS | OPTIONAL ACTIONS | SOFTWARE | AUTOMATION OR AI TOOL USED | NOTES
Onboarding |  | ONBOARDING (runs prior to first batch - see Standard Timeline)
Onboarding | Onboarding Team (CoS and OC) |  | Client Signs contract |  | Nusii
Onboarding | Onboarding Team |  | Share KO Survey |  | Google Forms
Onboarding | Onboarding Team |  | Create External Slack with Client |  | Slack
Onboarding | Onboarding Team |  | Recieve & Review KO Survey |  | Google Forms
Onboarding | Producer |  | Create New Client Portal/Calendar |  | Notion
Onboarding | Producer |  | Fill Out New Client Portal |  | Notion
Onboarding | Producer |  | Create Template Client Space in ClickUp |  | ClickUp
Onboarding | Producer |  | Fill Out new ClickUp Space with client information |  | ClickUp
Onboarding | Producer |  | Create Internal Slack Channel & Invite Team Members (CD PPM Editors Production ECD CoS CEO Hol HoP) |  | Slack
Onboarding | Producer |  | Ask for availability |  | Slack
Onboarding | Producer |  | Schedule Intro Call |  | Slack, Zoom
Onboarding | Producer |  | Schedule Channel Strategy Kickoff Call |  | Slack, Zoom
Onboarding | Producer |  | Gain Access to YT Channel |  | YouTube
Onboarding | Producer |  | Confirm Channel Analytics & Sample Footage was recieved |  | YouTube
Onboarding | CS |  | DA reviews YT Channel for Channel Audit |  | YouTube
Onboarding | CS |  | DA reviews competitors |  | YouTube
Onboarding | CS |  | DA assembles Channel Audit Report |  | Google Sheets, Notion, ClickUp
Onboarding | CS |  | DA shares Channel Audit with ECD and CD |  | Google Sheets, Notion, ClickUp
Onboarding | ECD & CD |  | ECD and CD Review & Align |  | Google Sheets, Notion, ClickUp, Slack
Onboarding | ECD & CD |  | ECD and CD Provide Feedback or Contribute Thoughts |  | Google Sheets, Notion, ClickUp, Slack
Onboarding | CS |  | DA revises |  | Google Sheets, Notion, ClickUp
Onboarding | CS |  | DA shares Channel Audit with ECD and CD |  | Google Sheets, Notion, ClickUp, Slack
Onboarding | ECD |  | ECD Approves |  | Google Sheets, Notion, ClickUp, Slack
Onboarding | ECD |  | Introduction Call (client provides feedback on Channel Audit) |  | Zoom
Onboarding | CS |  | DA revises Channel Audit |  | Google Sheets, Notion, ClickUp
Onboarding | CS |  | DA shares Channel Audit with ECD and CD |  | Google Sheets, Notion, ClickUp, Slack
Onboarding | ECD |  | ECD and CD Approve |  | Google Sheets, Notion, ClickUp, Slack
Onboarding | CD |  | CD creates Channel Content Strategy |  | Notion, YouTube Studio
Onboarding | CD |  | CD develops visual treatment options by online research and DA's past audit/analysis |  | Notion, YouTube Studio
Onboarding | CD |  | CD shares Content Strategy and Visual Treatment Options to ECD |  | Notion, Slack, ClickUp
Onboarding | ECD |  | ECD Approves or shares Feedback |  | Notion, Slack, ClickUp
Onboarding | CD |  | If Feedback Provided --> | CD Revises | Notion, YouTube Studio
Onboarding | CD |  |  | CD shares with ECD | Notion, Slack, ClickUp
Onboarding | ECD |  |  | ECD Approves | Notion, Slack, ClickUp
Onboarding | CD |  | CD adds Channel Audit Report, Analysis, Value Prop to new Onboarding Document |  | Google Sheets, Notion
Onboarding | CD |  | CD & ECD review onboarding dashboard |  | Notion, ClickUp
Onboarding | ECD |  | ECD revises final dashboard |  | Notion, ClickUp
Onboarding | ECD (+ Producer, CD) |  | Channel Kickoff Call commences |  | Zoom
Onboarding / Pre-Pro Overlap | CD |  | CD develops and shares Style Brief |  | ClickUp, Notion, YouTube, ViewStats, 1of10
Onboarding / Pre-Pro Overlap | PPM / Editor |  | PPM or Editor creates Style Edit |  | Adobe Premiere, Adobe After Effects
Onboarding / Pre-Pro Overlap | PPM / Editor |  | PPM or Editor Iterates on Style Edit |  | Adobe Premiere, Adobe After Effects
Onboarding / Pre-Pro Overlap | PPM |  | PPM Reviews |  | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | PPM |  | PPM Shares Feedback or Revises Themself |  | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | CD |  | CD Reviews Style Edit |  | Adobe Premiere, Adobe After Effects
Onboarding / Pre-Pro Overlap | CD |  | CD Approves or provides feedback |  | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | PPM / Editor |  | If Feedback Provided --> | PPM / Editor reviews feedback | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | PPM / Editor |  |  | PPM / Editor Revises | Adobe Premiere, Adobe After Effects
Onboarding / Pre-Pro Overlap | CD |  |  | CD Reviews and Approves | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | ECD |  | ECD Reviews Style Edit |  | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | PPM |  | ECD Approves or Provides Feedback |  | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | PPM / Editor |  | If Feedback Provided --> | PPM / Editor reviews feedback | Frame.io
Onboarding / Pre-Pro Overlap | PPM / Editor |  |  | PPM / Editor Revises | Adobe Premiere, Adobe After Effects
Onboarding / Pre-Pro Overlap | ECD |  |  | ECD Approves Style Edit | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | Producer |  | Share Style Edit to Client |  | Slack, Frame.io
Onboarding / Pre-Pro Overlap | Client |  | Client Approves or Provides Feedback |  | Slack, Frame.io
Onboarding / Pre-Pro Overlap | PPM / Editor |  | If Feedback Provided --> | PPM or Editor Revises | Adobe Premiere, Adobe After Effects
Onboarding / Pre-Pro Overlap | ECD |  |  | ECD and CD Approve Style Edit | Frame.io, ClickUp
Onboarding / Pre-Pro Overlap | Producer |  |  | Share Style Edit to Client | Slack, Frame.io
Onboarding / Pre-Pro Overlap | Client |  |  | Client Approves | Slack
Onboarding / Pre-Pro Overlap | Producer |  | Producer Updates Clickup |  | Slack, ClickUp
Onboarding / Pre-Pro Overlap | PPM |  | PPM assembles Editing SOP referencing Style Edit & Brief |  | Notion
Onboarding / Pre-Pro Overlap | Producer |  | Producer shares Editing SOP to ECD |  | Notion
Onboarding / Pre-Pro Overlap | ECD |  | ECD Reviews |  | Notion, Slack, ClickUp
Onboarding / Pre-Pro Overlap | ECD |  | ECD approves or provides feedback |  | Notion, Slack, ClickUp
Onboarding / Pre-Pro Overlap | CD |  | If Feedback Provided --> | CD Revises | Notion
Onboarding / Pre-Pro Overlap | CD |  |  | CD shares with ECD | Notion, Slack, ClickUp
Onboarding / Pre-Pro Overlap | ECD |  |  | ECD Approves | Notion, Slack, ClickUp
Pre-Production |  | Producer Programs New Batch of Content |  |  | ClickUp, Make | ClickUp - New Parent Tasks for Production Timeline Automation triggers Make - Production Timeline Automation (unsure what this is meant to do)
Pre-Production | Producer |  | Producer applies template batch to client space in ClickUp |  | ClickUp, Make | Make - Creation of Subtasks in Editing Batches (auto names tasks) + Click Up - Creation of Subtasks in Editing Parents (sends webhook when status changes to ready to start and task is Video or Short)
Pre-Production | Producer |  |  | Producer customizes it depending on client unique needs | ClickUp, Notion, Slack
Pre-Production | Producer |  | Producer sets publish dates |  | ClickUp
Pre-Production | Producer |  | Producer sets due dates by back tracking on publish dates |  | ClickUp
Pre-Production | Producer |  | Producer asks for client availability |  | ClickUp, Slack
Pre-Production | Producer |  | Producer cross references team availability |  | ClickUp, Google Calendar, Slack
Pre-Production | Producer |  | Producer adjusts |  | ClickUp
Pre-Production | Producer |  | Producer assigns tasks |  | ClickUp, Make | Make - Auto-Link Editor Via Relationship (Links Editor to Editor Database when Edit V1 is assigned)
Pre-Production | Producer |  | Producer & YPC add creative details as they're made available |  | ClickUp, Slack
Pre-Production |  | Batch is ready to begin |  |  |  | ClickUp - Task Dependency Update (CU based automation that makes one task "Ready to start" when the dependencies are cleared.
Pre-Production | CD |  | CD ideates and creates doc in Notion |  | ClickUp, Notion, YouTube, ViewStats, 1of10
Pre-Production | CD |  |  | Research ViewStats and/or 1of10 for Outliers and Trends. | Notion, ViewStats, 1of10
Pre-Production | CD |  |  | Reviews compariable content on YouTube | YouTube, Notion
Pre-Production | CD |  | CD confirms ideation is complete |  | Notion, ClickUp
Pre-Production | Producer |  | Producer passes onto Client |  | Slack, ClickUp
Pre-Production | Client |  | Client reviews |  | Slack, Notion
Pre-Production | Client |  | Client approves or provides feedback |  | Slack
Pre-Production | CD |  | If feedback provided --> | CD Revises | Notion
Pre-Production | CD |  |  | CD Confirms | Notion, Slack, ClickUp
Pre-Production | Producer |  |  | Producer Passes to Client | Slack, Notion
Pre-Production | Client |  |  | Client Reviews | Notion
Pre-Production | Client |  |  | Client Approves | Slack
Pre-Production | Client |  | Client records Voice Notes (Unless Client Longform is a Vlog) |  | Notta
Pre-Production | Client |  | Client shares Voice Notes |  | Dropbox, Slack, Notta
Pre-Production | Client |  | Producer Updates Clickup |  | Slack, ClickUp
Pre-Production |  | Scripting
Pre-Production | Producer |  | Producer links Voice Notes to ClickUp |  | ClickUp, Slack, Notta
Pre-Production | CD |  | CD quickly reviews Voice Notes |  | Notta, ChatGPT, Slack, Notion, ClickUp
Pre-Production | Script Writer |  | Script Writer reviews script using Voice Notes, Ideation Doc |  | Notta, ChatGPT, Slack, Notion, ClickUp
Pre-Production | Script Writer |  | Script Writer drafts script V1 using Voice Notes, Ideation Doc |  | Notta, ChatGPT, Slack, Notion, ClickUp
Pre-Production | CD |  | CD reviews V1 |  | Slack, Notion, ClickUp
Pre-Production | CD |  | CD approves or provides feedback |  | Slack, Notion, ClickUp
Pre-Production | Script Writer |  | If feedback is provided --> | Scriptwriter revieves & reviews feedback | Slack, Notion, ClickUp
Pre-Production | Script Writer |  |  | Scriptwriter revises script V2 | Notta, ChatGPT, Slack, Notion, ClickUp
Pre-Production | Script Writer |  |  | Scriptwriter confirms V2 is complete | Slack, ClickUp
Pre-Production | CD |  |  | CD reviews V2 | Slack, Notion, ClickUp
Pre-Production | CD |  |  | CD approves | Slack, ClickUp
Pre-Production | Producer |  | Producer passes script to client |  | Slack, Notion, ClickUp
Pre-Production | Client |  | Client reviews |  | Slack, Notion
Pre-Production | Client |  | Client approves or provides feedback |  | Slack, Notion
Pre-Production | Producer |  | If feedback is provided --> | Producer shares feedback to scriptwriter | Slack, ClickUp
Pre-Production |  |  |  | CD might help guide feedback by leaving additional comments in notion | Slack, Notion
Pre-Production | Script Writer |  |  | Scriptwriter reviews & reviews feedback | Slack, Notion, ClickUp
Pre-Production | Script Writer |  |  | Scriptwriter revises script V3 | Notta, ChatGPT, Slack, Notion, ClickUp
Pre-Production | Script Writer |  |  | Scriptwriter confirms V3 is complete | Slack, ClickUp
Pre-Production | CD |  |  | CD reviews V3 | Slack, Notion, ClickUp
Pre-Production | CD |  |  | CD approves | Slack, ClickUp
Pre-Production | Producer |  |  | Producer passes script to client | Slack, Notion, ClickUp
Pre-Production | Client |  |  | Client approves | Slack, Notion
Pre-Production | Producer |  | Producer Updates ClickUp |  | Slack, Notion, ClickUp
Production |  | Recording
Production | Client |  | Client records script |  | Notion
Production | Client |  | Client uploads raw footage |  | Dropbox
Production | Client |  | Client passes link to team |  | Slack, Dropbox
Post-Production |  | QC Rough and Roadmap
Post-Production | YPC |  | YPC confirms it's the correct link and footage |  | Dropbox, Slack
Post-Production | YPC |  | If not correct --> | YPC updates the link / places into correct space | Dropbox
Post-Production | YPC |  | YPC puts link info in task |  | ClickUp, Dropbox
Post-Production | Editor |  | Editor downloads footage |  | Dropbox, Make | Make - Active Video Tracker (x3 - Old Tracking Automations)
Post-Production | Editor |  | Editor uploads footage to Descript |  | Descript
Post-Production | Editor |  | Editor reviews & cuts down footage to reasonale time |  | Adobe Premiere
Post-Production | Editor |  | Uploads Rough Cut to Descript (if not already edited in Descript) |  | Descript
Post-Production | Editor |  | If new --> | Editor reviews Edit SOP | Notion
Post-Production | Editor |  |  | Editor reviews Style Edit | Frame.io
Post-Production | Editor |  | Editor assembles Roadmap |  | Adobe After Effects
Post-Production | Editor |  | Editor reviews |  | Adobe After Effects
Post-Production | Editor |  | Editor exports |  | Adobe After Effects
Post-Production | Editor |  | Editor uploads to ClickUp, tags CD |  | Slack, ClickUp, Make, Zapier | Make - Weekly Accumulator (x3 - Various Steps in Editor Database Tracking). Plus Zapier - Missed Due Date Tracker for Subtasks (unsure what this does)
Post-Production |  | Thumbnail V1
Post-Production | Designer |  | Designer reviews Ideation Doc |  | Notion, ClickUp
Post-Production | Designer |  | Designer creates Thumbnails V1 |  | Adobe Photoshop, ChatGPT
Post-Production | Designer |  | Designer uploads to CU and confirms to team |  | ClickUp
Post-Production | CD |  | CD reviews |  | ClickUp
Post-Production | CD |  | CD provides feedback |  | ClickUp
Post-Production |  | CD Reviews
Post-Production | CD |  | CD reviews Roadmap |  | ClickUp
Post-Production | CD |  | CD reviews rough cut |  | Descript
Post-Production | CD |  | CD approves or provides feedback (comments on CU) |  | ClickUp, Descript
Post-Production | Editor |  | If roadmap feedback --> | If Roadmap needs revising, Editor reviews feedback | ClickUp
Post-Production | Editor |  |  | Editor updates Roadmap | Adobe After Effects
Post-Production | Editor |  |  | Editor shares back Revision | ClickUp
Post-Production | CD |  |  | CD or PPM reviews | ClickUp
Post-Production | CD |  |  | CD or PPM approves | ClickUp
Post-Production | Editor |  | If rough cut feedback --> | Editor applies feedback in V1 or CD edits themself | Descript, ClickUp
Post-Production |  | Edit V1
Post-Production | Editor |  | Editor prepares new project |  | Adobe Premiere
Post-Production | Editor |  | Editor imports Footage |  | Adobe Premiere, Dropbox, ClickUp
Post-Production | Editor |  | If same editor as RC --> | Editor collects XML from Descript or ClickUp and links to project | Descript, Adobe Premiere, ClickUp
Post-Production | Editor |  | If new editor --> | Editor downloads project with footage from Descript | Descript, Adobe Premiere, ClickUp
Post-Production | Editor |  | Editor reviews script |  | Notion
Post-Production | Editor |  | Editor pulls bytes |  | Adobe Premiere, Notion
Post-Production | Editor |  | Editor applies B-Roll |  | Adobe Premiere, Dropbox
Post-Production | Editor |  | Editor applies music |  | Adobe Premiere, Artlist
Post-Production | Editor |  | Editor applies SFX |  | Adobe Premiere, Artlist
Post-Production | Editor |  | Editor updates graphics |  | Adobe After Effects
Post-Production | Editor |  | Editor applies graphics |  | Adobe Premiere, Adobe After Effects
Post-Production | Editor |  | Editor applies FX |  | Adobe Premiere, Adobe After Effects
Post-Production | Editor |  | Editor reviews |  | Adobe Premiere
Post-Production | Editor |  | Editor provides link via Frame IO |  | Frame.io, Adobe Premiere
Post-Production | Editor |  | Editor shares team via ClickUp |  | ClickUp, Slack, Frame.io
Post-Production |  | PPM V1 Reviews
Post-Production | PPM |  | PPM reviews video |  | Frame.io, ClickUp
Post-Production | PPM |  | PPM leaves feedback |  | Frame.io, ClickUp
Post-Production |  | Thumbnail V2
Post-Production | Designer |  | Desginer reviews feedback |  | ClickUp
Post-Production | Designer |  | Designer revises |  | Adobe Photoshop, ChatGPT
Post-Production | Designer |  | Designer uploads to CU and confirms |  | ClickUp
Post-Production |  | Edit V2
Post-Production | Editor |  | Editor reviews feedback |  | Frame.io
Post-Production | Editor |  | Editor applies feedback |  | Adobe Premiere, Frame.io
Post-Production | Editor |  | Editor reviews |  | Adobe Premiere, Frame.io
Post-Production | Editor |  | Editor updates link & confirms |  | Adobe Premiere, Frame.io, ClickUp
Post-Production |  | PPM V2 Review
Post-Production | PPM |  | PPM pulls up video and reviews |  | Frame.io, ClickUp
Post-Production | PPM |  | PPM leaves feedback via comments on Frame IO |  | Frame.io
Post-Production | PPM |  | PPM confirms feedback is complete |  | ClickUp
Post-Production |  | CD V2 Review
Post-Production | CD |  | CD pulls up video and reviews |  | Frame.io, ClickUp
Post-Production | CD |  | CD leaves feedback via comments on Frame IO |  | Frame.io
Post-Production | CD |  | CD reviews thumbnails |  | ClickUp
Post-Production | CD |  | CD provides feedback |  | ClickUp
Post-Production | CD |  | CD confirms feedback is complete |  | ClickUp
Post-Production |  | Edit V3
Post-Production | Editor |  | Editor reviews feedback |  | Adobe Premiere, Frame.io
Post-Production | Editor |  | Editor applies feedback |  | Adobe Premiere
Post-Production | Editor |  | Editor reviews |  | Adobe Premiere, Frame.io
Post-Production | Editor |  | Editor updates link & confirms |  | Adobe Premiere, Frame.io, ClickUp
Post-Production |  | PPM V3 Review
Post-Production | PPM |  | PPM pulls up video and reviews |  | Frame.io, ClickUp
Post-Production | PPM |  | PPM approves |  | ClickUp
Post-Production |  | CD V3 Review
Post-Production | CD |  | CD pulls up video and reviews |  | Frame.io, ClickUp
Post-Production | CD |  | CD pulls up thumbnails and revies |  | ClickUp
Post-Production | CD |  | CD approves |  | ClickUp
Post-Production |  | Client Review
Post-Production | YPC |  | YPC shares link to Client |  | Slack, ClickUp
Post-Production | Client |  | Client reviews |  | Frame.io, Slack
Post-Production | Client |  | Client leaves feedback |  | Frame.io, Slack
Post-Production | YPC |  | If feedback not in Frame.io --> | YPC shares feedback to editor | Slack
Post-Production |  | Edit V4
Post-Production | Editor |  | Editor reviews feedback |  | Adobe Premiere, Frame.io
Post-Production | Editor |  | Editor applies feedback |  | Adobe Premiere
Post-Production | Editor |  | Editor reviews |  | Adobe Premiere
Post-Production | Editor |  | Editor updates link & confirms |  | Adobe Premiere, Frame.io, ClickUp
Post-Production |  | CD or PPM V4 Review
Post-Production | PPM |  | PPM or CD pulls up video and reviews |  | Frame.io, ClickUp
Post-Production | PPM |  | PPM or CD approves |  | ClickUp
Post-Production |  | Client Review
Post-Production | YPC |  | YPC shares link to Client |  | Slack, ClickUp, Frame.io
Post-Production | Client |  | Client reviews |  | Frame.io
Post-Production | Client |  | Client leaves feedback or approves |  | Frame.io, Slack
Post-Production | YPC |  | If feedback not in Frame.io --> | YPC shares feedback to editor & continues to revise | Slack, ClickUp
Post-Production |  | Publish Prep
Post-Production | Client |  | Client provides final approval |  | Frame.io, Slack
Post-Production | CD |  | CD highlights final Title and Thumbs |  | Notion
Post-Production | YPC |  | YPC downloads export from Frame.io |  | Frame.io, ClickUp
Post-Production | YPC |  | YPC uploads export to Dropbox |  | Dropbox
Post-Production | YPC |  | YPC adds link to production tracker |  | ClickUp, Dropbox
Post-Production | YPC |  | YPC pulls link for packaging doc |  | ClickUp, Notion
Post-Production | YPC |  | YPC notifies publisher (grace) with tracker and packaging info |  | Slack, ClickUp
Post-Production | Publisher |  | Publisher downloads video |  | Dropbox, Slack, ClickUp
Post-Production | Publisher |  | Publisher uploads to youtube |  | YouTube
Post-Production | Publisher |  | Publisher adds metadata |  | YouTube, Notion, ClickUp
Post-Production | Publisher |  | Publisher schedules |  | YouTube, ClickUp
Post-Production | Publisher |  | Publisher confirms |  | Slack, ClickUp
Post-Production |  | Publish Split Test
Post-Production | CD |  | CD reviews A/B test results |  | YouTube, ClickUp
Post-Production | CD |  | CD updates thumbnail and then iterates with different copy |  | YouTube, Notion
Post-Production | CD |  | CD notes analytics |  | YouTube, Notion
Post-Production | CD |  | Later, CD reviews A/B test results again |  | YouTube, ClickUp
Post-Production | CD |  | CD updates with successful copy |  | YouTube, Notion
Post-Production | CD |  | CD notes analytics |  | YouTube, Notion
Post-Production |  | Monthly Report
Post-Production | CD |  | CD locates and reviews Brief Template for date accuracy, LF vs. SF |  | Notion, YouTube, ClickUp
Post-Production | CD |  | CD reviews specific YT Video Performance |  | YouTube, 1of10, ViewStats, Notion
Post-Production | CD |  | CD adds questions for DA to muse on in Notion, confirms when done |  | Notion, ClickUp
Post-Production | CS |  | Data Analyst reviews CD's brief |  | Notion, ClickUp
Post-Production | CS |  | Data Analyst executes report |  | Notion, ClickUp, YouTube, ViewStats, 1of10
Post-Production | CS |  | Data Analyst shares report |  | ClickUp, Slack, Notion